## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2025 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  | 2026-10-05
Project Team Name |  | Group 6 (Cogni)
Project Topic |  | Bayan: Arabic text simplification assistant for readers with dyslexia
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[8 empty] | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05
1. Project initiation and planning |  |  | 2026-09-16 | 2026-09-22 | Marwan, Abdulrahman |  | Done
| 1.1. Project brief and reference architecture |  | 2026-09-16 | 2026-09-16 | Abdulrahman | Brief, architecture report | Done
| 1.2. Verified literature and benchmark references |  | 2026-09-16 | 2026-09-17 | Marwan | Reference library | Done
| 1.3. Action Plan draft |  | 2026-09-17 | 2026-09-19 | Marwan | Action Plan draft | Done
| 1.4. Execution plan: 13 milestones with risks and mitigations |  | 2026-09-16 | 2026-09-16 | Abdulrahman | Execution plan | Done
| 1.5. Final Action Plan, every claim labelled measured / decided / planned (#25) |  | 2026-09-21 | 2026-09-22 | Marwan | Final Action Plan | Done
2. Project management |  |  | 2026-09-17 | 2026-10-04 | Marwan |  | Done
| 2.1. Team setup: repository, workflow and roles |  | 2026-09-17 | 2026-09-18 | Marwan | Repository, team guidance | Done
| 2.2. Risk register and data contingency plan |  | 2026-09-18 | 2026-09-19 | Marwan | Risk register | Done
| 2.3. Product form decision record: Android plugin, on device (#9) |  | 2026-09-20 | 2026-09-20 | Marwan, Mohammed | Decision record | Done
| 2.4. Task issues with handoffs, and pull-request reviews |  | 2026-09-19 | 2026-10-04 | Marwan | GitHub issues, reviews | Done
| 2.5. Mentoring sessions: progress shown (23 and 30 Sep) |  | 2026-09-23 | 2026-09-30 | Marwan | Progress reports | Done
3. Data |  |  | 2026-09-16 | 2026-10-04 | Abdulrahman, Marwan, Ahmed |  | Done
| 3.1. BAREC readability analysis |  | 2026-09-16 | 2026-09-16 | Abdulrahman | Analysis report | Done
| 3.2. Reading-level classifier, ONNX int8 (CAMeL AraBERT) (#17, #20) |  | 2026-09-16 | 2026-09-21 | Abdulrahman | Level classifier | Done
| 3.3. Equivalence validator and easy-band gate |  | 2026-09-16 | 2026-09-20 | Abdulrahman | Validator, gate | Done
| 3.4. Synthetic data pipeline A (DeepSeek on BAREC) |  | 2026-09-16 | 2026-09-16 | Abdulrahman | Pipeline A | Done
| 3.5. Pipeline A 10% run: 3,010 sentences scored, 5,054 clean pairs |  | 2026-09-16 | 2026-09-17 | Abdulrahman | Generated pairs v1 | Done
| 3.6. Synthetic data pipeline B (Gemini and Gemma): 5,618 checked pairs |  | 2026-09-18 | 2026-09-19 | Marwan | Synthetic dataset v1 | Done
| 3.7. Shared data format specification |  | 2026-09-19 | 2026-09-19 | Marwan, Abdulrahman | Format spec | Done
| 3.8. Word-difficulty lexicon (24,458 words) |  | 2026-09-20 | 2026-09-20 | Abdulrahman | Lexicon | Done
| 3.9. Validation module (scripts/validation.py) (#10, #11) |  | 2026-09-19 | 2026-09-20 | Abdulrahman, Marwan | Validation module | Done
| 3.10. Human review set (500 pairs) and annotation tool |  | 2026-09-20 | 2026-09-20 | Abdulrahman | Review set, tool | Done
| 3.11. SAMER corpus in the shared format (#5) |  | 2026-09-19 | 2026-09-21 | Ahmed | SAMER dataset | Done
| 3.12. Leakage audit: 9.3% of Baseet in the locked test sets; leakage gate |  | 2026-09-21 | 2026-09-21 | Marwan | Audit, clean data | Done
| 3.13. Re-labelled synthetic export (#12) |  | 2026-09-20 | 2026-09-25 | Abdulrahman | Re-labelled export | Done
| 3.14. BayanSimplify-v0.2 training data: 22,733 tagged, meaning-filtered pairs |  | 2026-09-22 | 2026-09-24 | Marwan | Training set | Done
| 3.15. Synthetic corpus v0 exported and published: 13,072 pairs (#8, #38, #42) |  | 2026-09-25 | 2026-09-30 | Abdulrahman | Corpus v0 (Hub) | Done
| 3.16. Corpus v1: Gemma 4 generator, Qwen judge, 14,975 rows, data card (#44, #45) |  | 2026-09-28 | 2026-10-04 | Abdulrahman | Corpus v1, data card | Done
4. Models |  |  | 2026-09-19 | 2026-10-05 | Ahmed, Sanad, Abdulrahman, Marwan |  | Done
| 4.1. Diacritization benchmark; Libtashkeel selected (#6, #23) |  | 2026-09-19 | 2026-09-21 | Sanad | Benchmark report | Done
| 4.2. Read-aloud model selection: Nabra-7M-Distill |  | 2026-09-21 | 2026-09-22 | Marwan | Selection | Done
| 4.3. BayanSimplify-v0.1: AraT5v2 on SAMER, trained and documented (#5, #22) |  | 2026-09-19 | 2026-09-23 | Ahmed | BayanSimplify-v0.1 | Done
| 4.4. BayanSimplify-v0.1 diagnosis on the locked test sets |  | 2026-09-22 | 2026-09-23 | Marwan | Diagnosis | Done
| 4.5. BayanSimplify-v0.2: AraT5v2 on the tagged mix (#28, #40) |  | 2026-09-24 | 2026-09-25 | Ahmed | BayanSimplify-v0.2 | Done
| 4.6. BayanSimplify-v0.2-Fast: AraBART on the same mix, and the speed benchmark (#29, #35) |  | 2026-09-24 | 2026-09-25 | Sanad | BayanSimplify-v0.2-Fast | Done
| 4.7. Meaning judge: Gemma 4 E2B, four heads, three variants (#47, #49) |  | 2026-09-30 | 2026-10-04 | Abdulrahman | Meaning judge (Hub) | Done
| 4.8. BayanSimplify-v0.3: AraT5v2 on corpus v1, int8 bundle (#48, #53) |  | 2026-10-02 | 2026-10-04 | Abdulrahman | BayanSimplify-v0.3 | Done
| 4.9. BayanSimplify models published on Hugging Face, with the ONNX bundles |  | 2026-10-05 | 2026-10-05 | Marwan | Public models (Hub) | Done
5. Evaluation |  |  | 2026-09-19 | 2026-10-05 | Abdul Majid, Marwan |  | Done
| 5.1. Scoring harness and locked test sets (#7, #15, #16, #18) |  | 2026-09-19 | 2026-09-21 | Abdul Majid, Marwan | Scripts, manifest | Done
| 5.2. Copy baselines, locked-set converter, generate-and-score path (#19, #24, #26) |  | 2026-09-21 | 2026-09-22 | Abdul Majid | Baselines | Done
| 5.3. BayanSimplify-v0.2 scoring tools (#33, #34) |  | 2026-09-24 | 2026-09-24 | Marwan, Abdul Majid | Scoring tools | Done
| 5.4. BayanBench v1: behaviour tracks, document split; v0.2 scored on test |  | 2026-09-26 | 2026-09-28 | Marwan, Abdul Majid | BayanBench v1 | Done
| 5.5. BayanBench v2: open meaning scorer (Gemma 4 31B); all systems scored (#48) |  | 2026-09-29 | 2026-09-30 | Marwan, Abdulrahman | BayanBench v2 | Done
| 5.6. Human rating round: 290 tasks, five raters and a reader with dyslexia (#48) |  | 2026-09-30 | 2026-10-03 | Marwan, Sanad, Ahmed, Mohammed, Ibrahim (Dyslexic Reader) | Ratings, scorer check | Done
| 5.7. BayanBench v2.0 frozen; test split scored (#55) |  | 2026-10-03 | 2026-10-04 | Marwan, Abdulrahman | BayanBench v2.0 | Done
| 5.8. BayanSimplify-v0.3 ship gate; with four beams it becomes the large model (#56, #59, #68) |  | 2026-10-04 | 2026-10-05 | Marwan, Abdulrahman | Decision | Done
| 5.9. Benchmark report: 35 systems on BayanBench v2.0 (#57, #58) |  | 2026-10-03 | 2026-10-04 | Abdulrahman | Benchmark report | Done
| 5.10. Rating round for the app's three models: five raters, blind |  | 2026-10-04 | 2026-10-05 | Marwan, Sanad, Ahmed, Mohammed | Ratings | Done
| 5.11. Diacritization re-benchmark: earlier numbers reproduce (#67) |  | 2026-10-04 | 2026-10-05 | Marwan, Sanad | Re-benchmark | Done
6. Application |  |  | 2026-09-20 | 2026-10-05 | Mohammed, Marwan |  | Done
| 6.1. PROCESS_TEXT plugin and result sheet (#14, #21) |  | 2026-09-20 | 2026-09-21 | Mohammed | Android plugin | Done
| 6.2. Model download, result states, settings, typography (#31, #37) |  | 2026-09-24 | 2026-09-30 | Mohammed | App features | Done
| 6.3. Compose app with Material 3 Expressive (#37) |  | 2026-09-26 | 2026-09-30 | Marwan | App | Done
| 6.4. Read-aloud with word highlighting (Nabra through sherpa-onnx) |  | 2026-09-27 | 2026-09-30 | Marwan | Read-aloud | Done
| 6.5. Overlay, floating reader, text-step guards, Bayan design system (#54) |  | 2026-10-01 | 2026-10-04 | Marwan | App release | Done
| 6.6. Beam search as a per-model decoding option (#61, #62) |  | 2026-10-04 | 2026-10-04 | Marwan | Decoder | Done
| 6.7. BayanSimplify-v0.3 as the large model, four beams on by default; safety net (#66) |  | 2026-10-04 | 2026-10-05 | Marwan | App release | Done
| 6.8. Tashkeel in the app: Libtashkeel bundled (#67) |  | 2026-10-04 | 2026-10-05 | Marwan | Tashkeel setting | Done
| 6.9. Design system in the repository (#69) |  | 2026-10-05 | 2026-10-05 | Marwan | Design system | Done
7. On-device model |  |  | 2026-09-24 | 2026-10-04 | Marwan |  | Done
| 7.1. ONNX export, int8 quantization, on-device engine (#32) |  | 2026-09-24 | 2026-09-26 | Marwan | Model bundles | Done
| 7.2. Phone latency: AraT5v2 (26 Sep), AraBART (3 Oct), beam search (4 Oct) |  | 2026-09-26 | 2026-10-04 | Marwan | Measurements | Done
8. Final deliverables |  |  | 2026-09-29 | 2026-10-06 | Marwan, Abdulrahman |  | Done
| 8.1. Final report (#52, #70) |  | 2026-09-29 | 2026-10-05 | Marwan, Abdulrahman | Final report | Done
| 8.2. Pitch deck (#50) |  | 2026-10-02 | 2026-10-05 | Abdulrahman | Slide deck | Done
| 8.3. Coding reference: repository and README (#60, #70) |  | 2026-10-04 | 2026-10-05 | Marwan | Repository | Done
| 8.4. Demo video |  | 2026-10-04 | 2026-10-05 | Abdulrahman | Demo video | Done
| 8.5. Final pitch (Tue 6 Oct), presented by Sanad |  | 2026-10-06 | 2026-10-06 | Sanad | Pitch | In-progress
Formulas:
Start date = MIN([Start date, row below]:F19)
End date = MAX([End date, row below]:G19)